## 工作表1
Phase | Assign To | Category | App | Task | Status | Description
1 | Developer A | Master Data | misc | Vendor Maint Screen
1 |  | Overall | N/A | Look & Feel |  | Look & Feel, Navigation, Flow
1 | Developer B | Sales | sales | Sales Order Portal Screen
1 | Developer B | Sales | sales | Sales Order Screen |  | Create and Update Sales Order
1 | Developer B | Sales | sales | Item Measurement Screen |  | Consider this as part of sales order screen
1 | Developer A | Master Data | misc | Fabric Maint Screen |  | Create and Update Fabric Record
1 | Developer C | Master Data | misc | Customer Portal Screen
1 | Developer C | Master Data | misc | Customer Screen |  | Register, Modify, Update both customer info and actual measurement
2 | Developer B | Order Processing | po | LPO Portal Screen |  | Export to Excel, Showing a list of order, Need Filter Function
2 | Developer B | Order Processing | po | LPO Screen |  | Update both main and detail table in 1 secreen, PDF Export
2 | Developer B | Order Processing | po | Create LPO Screen |  | Create the order. Check ER Diagram for the data relationship
2 | Developer A | Order Processing | po | APO Portal Screen |  | Export to Excel, Showing a list of order, Need Filter Function
2 | Developer A | Order Processing | po | APO Screen |  | Update both main and detail table in 1 secreen, PDF Export
2 | Developer A | Order Processing | po | Create APO Screen |  | Create the order. Check ER Diagram for the data relationship
2 | Developer C | Order Processing | po | FPO Portal Screen |  | Export to Excel, Showing a list of order, Need Filter Function
2 | Developer C | Order Processing | po | FPO Screen |  | Update both main and detail table in 1 secreen, PDF Export
2 | Developer C | Order Processing | po | Create FPO Screen |  | Create the order. Check ER Diagram for the data relationship
2 | Developer A | Order Processing | sales, po | Excel and PDF |  | For all PO and sales order screens
2 | Developer A | Sales | sales | Sales Order Invoice and Receipt (PDF)
2 | Developer A | Global function | misc | Master Search function |  | A search box for search any LPO, APO, FPO, and Sales Order based on prefix identifier. Put this on the top menu item. And need to build a result page.